## Sheet1
Dimension Name | Level | Unique ID | Capability | Predecessor | Changed from
Strategy Alignment | Traveller | 1 | Any alignment to Strategy is coincidental or opportunistic | 0
Strategy Alignment | Artisan | 2 | Upfront engagement with stakeholders to ensure Business and Technical Alignment | 1
Strategy Alignment | Artisan | 3 | The product/project vision is explicitly aligned to strategy | 1
Strategy Alignment | Artisan | 4 | Post implementation view to confirm strategy alignment | 1
Strategy Alignment | Expert | 5 | Occasional engagement with stakeholders throughout delivery cycle to review business and technical alignment | 2,3,4
Strategy Alignment | Expert | 6 | Backlog items are created to deal with strategy alignment issues | 0
Strategy Alignment | Professional | 7 | Frequent engagement with Stakeholders to review Business and technical alignment | 5
Strategy Alignment | Professional | 8 | Team presents product to Architecture and Design teams with the intent of picking up alignment issues | 5
Strategy Alignment | Professional | 9 | Metrics to measure strategy elements defined and tracked | 0
Strategy Alignment | Master | 10 | All major strategy alignment backlog items have been resolved | 6
Strategy Alignment | Master | 11 | All requirements are attached to business metric | 9
Strategy Alignment | Master | 12 | Metrics are tracked over time and improvements targets are set and achieved | 9
Strategy Alignment | Master | 13 | Team independently innovates by creating new features or optimisations in support of or extending the strategy. | 9
Planning and Requirements | Traveller | 14 | Team is not involved in estimates | 0
Planning and Requirements | Traveller | 15 | No Specific prioritization of requirements | 0
Planning and Requirements | Traveller | 16 | Iteration lengths are erratic and based on the amount of functionality | 0
Planning and Requirements | Traveller | 17 | The team does not know their velocity | 0
Planning and Requirements | Traveller | 18 | No Stakeholder management in place | 0
Planning and Requirements | Artisan | 19 | Team performs estimates up-front | 14
Planning and Requirements | Artisan | 20 | Requirements are prioritized based on business value | 15
Planning and Requirements | Artisan | 21 | Iteration lengths are fixed | 16
Planning and Requirements | Artisan | 22 | The team knows their velocity | 17
Planning and Requirements | Artisan | 23 | Stakeholders have been identified and a formal communication plan is in place | 18
Planning and Requirements | Expert | 24 | Team performs estimation iteratively | 19
Planning and Requirements | Expert | 25 | The MVP and MVPS have been identified | 20
Planning and Requirements | Expert | 26 | The teams velocity is predictable | 22
Planning and Requirements | Expert | 27 | All backlog items are sized by the teams | 0
Planning and Requirements | Expert | 28 | Stakeholders attend showcase | 23
Planning and Requirements | Professional | 29 | Team tracks performance against estimates | 24
Planning and Requirements | Professional | 30 | Requirements are developed on a just –in –time basis | 25
Planning and Requirements | Professional | 31 | Analytics are implemented to determine the effectiveness of requirements | 25
Planning and Requirements | Professional | 32 | The amount of functionality for each iteration is determined by the teams velocity | 26
Planning and Requirements | Professional | 33 | Technical debt and defects are tracked on the backlog and form part of the estimated team velocity | 27
Planning and Requirements | Professional | 34 | Stakeholders actively participate in retrospective | 28
Planning and Requirements | Master | 35 | Requirements are defined with an expected outcome with an objective measure | 30,31
Planning and Requirements | Master | 36 | Release planning is performed based on the teams current velocity | 32,33
Planning and Requirements | Master | 37 | A formal beta program is in place to allow extended stakeholders and customers to evaluate the software and provide feedback. | 34
Coding Practices | Traveller | 38 | No standards or mechanism's for ensuring code quality | 0
Coding Practices | Artisan | 39 | Standards are defined but they are inconsistently applied | 38
Coding Practices | Artisan | 40 | Consistent training process for new team members is in place | 0
Coding Practices | Expert | 41 | There are mechanism’s in place to ensure that standards are followed | 39
Coding Practices | Expert | 42 | Process's and practices are understood and followed by all | 40
Coding Practices | Expert | 43 | Metrics are defined but not necessarily reviewed and acted on | 0
Coding Practices | Expert | 44 | The team proactively improves the code | 0
Coding Practices | Professional | 45 | Code metrics are part of build automation and continuous integration | 43
Coding Practices | Professional | 46 | Code metrics are tracked for trends and adjustments made on a continuous basis | 43
Coding Practices | Professional | 47 | The team regularly performs katas with the objective of improving their skills | 44
Coding Practices | Professional | 48 | Code is regularly refactored as part of the iteration | 44
Coding Practices | Master | 49 | Standards and Practices are regularly reviewed and updated | 41
Coding Practices | Master | 50 | Processes and Practices are regularly reviewed and updated | 42
Coding Practices | Master | 51 | The code metrics are assessed and backlog items created to drive improvement | 45,46
Coding Practices | Master | 52 | Technical debt is minimized | 0
Continuous Integration | Traveller | 53 | No version management of artefacts and reports | 0
Continuous Integration | Traveller | 54 | Deployments & Rollbacks are manual | 0
Continuous Integration | Traveller | 55 | Build is performed manually and infrequently. | 0
Continuous Integration | Traveller | 56 | Build is owned by a specific person | 0
Continuous Integration | Traveller | 57 | Testing is manual | 0
Continuous Integration | Traveller | 58 | Development environments manually provisioned and shared between teams | 0
Continuous Integration | Artisan | 59 | Source code is under version management | 53
Continuous Integration | Artisan | 60 | Build is automated and tests are run as part of the build | 55
Continuous Integration | Artisan | 61 | Testing partially automated – less than 50% code coverage. | 57
Continuous Integration | Expert | 62 | Team checks code into version management system on daily basis. | 59
Continuous Integration | Expert | 63 | All artefacts are under version management. | 59
Continuous Integration | Expert | 64 | Build and Deployment to development environment are automated. | 54,60
Continuous Integration | Expert | 65 | Anyone in the team can start build at any point in time | 56
Continuous Integration | Expert | 66 | Build status and broken builds are visible to all. | 0
Continuous Integration | Expert | 67 | Testing partially automated – greater than 50% code coverage. | 61
Continuous Integration | Expert | 68 | Release and Change Management partially automated. | 0
Continuous Integration | Professional | 69 | Automated build and test cycle every time a change is committed | 64
Continuous Integration | Professional | 70 | Build metrics gathered, visible, and acted on. Builds are not left broken and code is not committed on a broke build. | 0
Continuous Integration | Professional | 71 | Deployment to test environment is automated. | 66
Continuous Integration | Professional | 72 | Non-functional testing is automated. | 66
Continuous Integration | Professional | 73 | Testing is automated as much as is practical. | 66
Continuous Integration | Professional | 74 | Environments can be provisioned at on demand. | 58
Continuous Integration | Master | 75 | Build and deployment are automated as much as is practical | 68
Continuous Integration | Master | 76 | The build pipeline extends directly into production | 68
Continuous Integration | Master | 77 | Tests are run in parallel across multiple machines | 70,71.72
Continuous Integration | Master | 78 | Trunk-based development is the standard practice and integration happens continuously. Branches are rarely created and are short lived. | 0
Continuous Integration | Master | 79 | Check-ins occur multiple times each day. | 0
Continuous Integration | Master | 80 | Environment & infrastructure specifications are managed and versioned along with all other artefacts. | 73
Continuous Integration | Master | 81 | The CI build creates and provisions environments to allow scalability for testing. | 73
Continuous Integration | Master | 82 | Release and Change Management fully integrated into deployment processes. | 67
Continuous Integration | Master | 83 | The product is always in releasable state. | 67
Continuous Integration | Master | 84 | Automated release process, release to customers is a business decision. | 67
Incident Management | Traveller | 85 | The process for handling problems and incidents is ad-hock. | 0
Incident Management | Artisan | 86 | An incident management process is in place and understood, but probably inconsistent. | 84
Incident Management | Artisan | 87 | Key people are identified for incident management. | 84
Incident Management | Artisan | 88 | High number of handoffs and multiple teams involved in incident resolution. | 0
Incident Management | Expert | 89 | Incidents and problems feed into backlog | 85
Incident Management | Expert | 90 | Operation requirements are identified and tracked in the backlog | 86
Incident Management | Expert | 91 | Problem management includes an urgency to address the root cause | 0
Incident Management | Expert | 92 | Root cause analysis is performed inconsistently | 0
Incident Management | Expert | 93 | Level 1, 2, 3 support structure in place | 87
Incident Management | Expert | 94 | Instrumentation (monitoring) in place. | 0
Incident Management | Professional | 95 | Defects are resolved once and deployed automatically across all environments. | 88,89
Incident Management | Professional | 96 | Defects resolution includes full regression tests | 88 89
Incident Management | Professional | 97 | System health is proactively monitored. | 88 89
Incident Management | Professional | 98 | Root cause analysis is mandatory and regularly trended. | 90,91
Incident Management | Master | 99 | Feature teams do own incident management | 94,95,96
Incident Management | Master | 100 | Fail Forward (failing in a way that enables you to identify and overcome underlying problem, encapsulates the way forward and reduce the likelihood of failure the next time around) | 94 95 96
Incident Management | Master | 101 | Feature Teams resolve issues themselves. | 92
Incident Management | Master | 102 | Team actively manages, monitors and reviews what happens in production, feedback loop is enabled and acted on. | 93
Risk and Issue Management | Traveller | 103 | Risk Management does not exist or is just a box to tick in order to get through a process (i.e. something done to keep risk and audit people happy). | 0
Risk and Issue Management | Traveller | 104 | There is no awareness or transparency of current risks and issues in the team. | 0
Risk and Issue Management | Artisan | 105 | Risks have been identified and are captured using an appropriate artefact such as a risk story wall or risk register. | 102
Risk and Issue Management | Artisan | 106 | Each identified risk has been assigned a risk mitigation or action plan. | 103
Risk and Issue Management | Artisan | 107 | Risks are discussed as part of the iteration planning process. | 103
Risk and Issue Management | Expert | 108 | Risks, issues and blockers are discussed and updated in appropriate detail as part of all sessions (stand-ups; iteration planning; showcases; steering committee meetings) | 104
Risk and Issue Management | Expert | 109 | Unmitigated or uncontrollable risks are easily identifiable. | 105 106
Risk and Issue Management | Expert | 110 | Risks, controls and action plans are assigned to appropriate owners: someone who understand the risk, has responsibility and accountability for managing the risk, and has the authority to implement controls and actions. | 0
Risk and Issue Management | Professional | 111 | The cost and benefits of risk mitigations are evaluated and recorded before they are implemented | 108
Risk and Issue Management | Professional | 112 | Risk management roles, responsibilities and accountabilities have been formally defines and agreed upon (such as in position descriptions and KRAs) | 109
Risk and Issue Management | Professional | 113 | The effective management of risks are considered a success criteria when implementing changes or new systems, processes and products. | 0
Risk and Issue Management | Professional | 114 | Regular check points with Business Stakeholders to ensure they are aware of all risks and issues. | 0
Risk and Issue Management | Professional | 115 | Time to resolve issues is tracked. | 0
Risk and Issue Management | Master | 116 | Risk mitigations and actions are explicitly designed to increase positive outcomes and reduce negative outcomes. | 110
Risk and Issue Management | Master | 117 | The business participates in developing mitigation strategies | 111
Risk and Issue Management | Master | 118 | Risk management is used to identify potential opportunities and drive strategy by thinking about risk in terms of uncertainty (which could be positive or negative) | 112
Risk and Issue Management | Master | 119 | Measures and metrics exist to demonstrate the effectiveness of risk management and where improvement is required. | 0
Risk and Issue Management | Master | 120 | The financial impact of risk and issues is clearly understood. | 0
Software Design | Traveller | 121 | Speculative design and technical decisions are made on an ad hoc basis. There is no vision or long team technical planning. | 0
Software Design | Traveller | 122 | BDUF = Big Design Up-Front | 0
Software Design | Traveller | 123 | Solutions are tightly coupled and brittle | 0
Software Design | Artisan | 124 | Regular design reviews in place | 120
Software Design | Artisan | 125 | Design assumptions are tracked and validated during iterations | 121
Software Design | Expert | 126 | Design issues are tracked and prioritised in the backlog. | 123
Software Design | Expert | 127 | Non-functional requirements are documented and tracked. | 124
Software Design | Expert | 128 | Clear interfaces defined between modules | 122
Software Design | Expert | 129 | Designer is a member of the feature team. | 0
Software Design | Professional | 130 | There is a partial traceability between design and requirements | 125
Software Design | Professional | 131 | Design requirements are expressed as automated tests | 0
Software Design | Professional | 132 | Non-functional requirements are defined and associated metrics tracked automatically. | 126
Software Design | Professional | 133 | Where practical all modules of the system can be simulated. | 127
Software Design | Professional | 134 | Where possible design is captured in a model and code generated. | 0
Software Design | Master | 135 | There is full traceability between design and requirements | 129
Software Design | Master | 136 | Design activities are performed on a Just In Time basis. | 129
Teaming | Traveller | 137 | The team cannot make decisions without consultation | 0
Teaming | Traveller | 138 | The teams goals and visions are unclear | 0
Teaming | Traveller | 139 | The team doesn't clearly understand the entire stakeholder landscape | 0
Teaming | Artisan | 140 | Team vision and goals are agreed, captured and understood. | 137
Teaming | Artisan | 141 | There is a clear understanding of who are the teams stakeholders. (Consumers, partners and clients) | 138
Teaming | Artisan | 142 | There is a clear definition of what the teams success is (definition of ‘done’) | 0
Teaming | Expert | 143 | The team actively seeks feedback in an effort to achieve the goals | 139
Teaming | Expert | 144 | Transparency and high level of collaboration are in place, both within the team and to and from the stakeholders. | 140
Teaming | Expert | 145 | Blockers and external dependencies are minimized and managed and the team knows what these are. | 141
Teaming | Professional | 146 | Balanced participation is in place. Team members contribute as appropriate and each members opinion is valued. | 143
Teaming | Professional | 147 | Team uses adequate measures to monitor success. | 144
Teaming | Master | 148 | All decision-making is internal to the team | 136
Teaming | Master | 149 | Complete collective ownership is in place, both when team is successful and when it fails, | 145
Teaming | Master | 150 | Team is actively improving. Retrospectives are driving improvement. | 146
Release Management | Traveller | 151 | Cycle time is extremely long. | 0
Release Management | Traveller | 152 | Deployment is mostly manual, very complex and requires high level of coordination between stakeholders on the day of the release | 0
Release Management | Traveller | 153 | Pace and delivery of work is inconsistent throughout the release cycle | 0
Release Management | Traveller | 154 | Separate build artefacts are created for each environment | 0
Release Management | Artisan | 155 | Releases are planned to a regular cycle and features are tracked and managed to the regular time frame, which is still relatively long. | 151
Release Management | Artisan | 156 | Planned release can extend close to the deadline because the team is not ready. | 152
Release Management | Artisan | 157 | Releases are still reliant on the skills and knowledge of key individuals | 0
Release Management | Artisan | 158 | Standard build artefacts are defined, and if they are produced, are created mostly by manual means (release notes, binaries, configurations, test coverage reports...) | 155
Release Management | Expert | 159 | Release cycles are planned on a regular schedule and seldom extended. The cycle time is shorter. | 156
Release Management | Expert | 160 | The confidence level for the release is high, but there is still reliance on individual skill to ensure the deployment will work in production. | 157, 158
Release Management | Expert | 161 | There is a formal process for handing the release to operations and support teams | 0
Release Management | Professional | 162 | Releases and deployments are mostly automated, but require manual configuration and coordination between teams. | 160
Release Management | Professional | 163 | Operations teams collaborate closely with the delivery team and contribute to minimize the risk of failure in production. | 162
Release Management | Professional | 164 | Release metrics and trends are tracked | 0
Release Management | Master | 165 | The team controls the release | 163
Release Management | Master | 166 | Releases can be deployed at any time and are fully automated. | 163
Release Management | Master | 167 | Release notes are automatically generated. | 163
Release Management | Master | 168 | The product owner is able to determine when release goes into production | 163
Release Management | Master | 169 | Operations team is part of the product/program team | 164
Release Management | Master | 170 | Release are Routine and not dependent on the talents of key individuals | 161
Release Management | Master | 171 | Dark launching is enabled. | 0
Quality Assurance | Traveller | 172 | Testing is manual | 0
Quality Assurance | Traveller | 173 | There is a high amount of rework due to testing late in the lifecycle. | 0
Quality Assurance | Traveller | 174 | Non-functional testing is not considered upfront. | 0
Quality Assurance | Traveller | 175 | Test cases are designed based only on the requirements document, mainly by testing team | 0
Quality Assurance | Traveller | 176 | Absence of unit/integration testing | 0
Quality Assurance | Traveller | 177 | There is very little reuse of Quality Assurance assets. | 0
Quality Assurance | Artisan | 178 | Regression test packs are partially automated | 172,173,174
Quality Assurance | Artisan | 179 | Regression packs run frequently but on an ad hoc basis | 172 173 174
Quality Assurance | Artisan | 180 | Test cases designed by the team, with testing, development and business analysts | 175
Quality Assurance | Expert | 181 | Regression test packs are fully automated | 180,181
Quality Assurance | Expert | 182 | Regression test packs are run as part of the build | 180 181
Quality Assurance | Expert | 183 | 50% coverage automated testing | 180 181
Quality Assurance | Expert | 184 | Automated smoke testing is in place | 180 181
Quality Assurance | Expert | 185 | Automated performance testing is in place | 180 181
Quality Assurance | Expert | 186 | Non-functional requirements are defined and measured | 0
Quality Assurance | Expert | 187 | Test cases designed by the team as part of the iteration | 182
Quality Assurance | Expert | 188 | Unit tests are created using TDD. | 0
Quality Assurance | Professional | 189 | Automated infrastructure testing is in place | 184 185 186 187 188
Quality Assurance | Professional | 190 | Automated security testing is in place | 184 185 186 187 188
Quality Assurance | Professional | 191 | Tests are automated as much as is practical | 184 185 186 187 188
Quality Assurance | Professional | 192 | Quality metrics and trends are tracked | 0
Quality Assurance | Professional | 193 | Anyone can execute the tests. | 0
Quality Assurance | Master | 194 | Active process is in place to understand root cause and respond to it. | 192,193,194
Quality Assurance | Master | 195 | Test artefacts are treated with the same importance as code and continually refactored and maintained. | 190
Quality Assurance | Master | 196 | Performance testing metrics are defined early in the process. | 195
Quality Assurance | Master | 197 | Tests drive release decisions | 0
Environments | Traveller | 198 | Data migrations un-versioned and performed manually. | 0
Environments | Traveller | 199 | Test data is not controllable | 0
Environments | Traveller | 200 | Environments are heavily governed | 0
Environments | Traveller | 201 | Environments are not refreshed regularly | 0
Environments | Traveller | 202 | Test environments and test data are frequently unavailable | 0
Environments | Traveller | 203 | Environments are provisioned manually | 0
Environments | Traveller | 204 | Key man dependencies | 0
Environments | Artisan | 205 | Changes are done with automated scripts versioned with application | 201
Environments | Artisan | 206 | A separate test environment maybe available, but is shared with other teams. | 202 203 204 205
Environments | Artisan | 207 | Tests are delayed due to other teams’ activities affecting the availability of the environment | 202 203 204 205
Environments | Artisan | 208 | An external group maintains the environment. | 202 203 204 205
Environments | Artisan | 209 | Test environments are available during specific dates/time slots | 202 203 204 205
Environments | Artisan | 210 | Ability to deploy basic virtual environments | 0
Environments | Artisan | 211 | Team has a dedicated development environment | 0
Environments | Expert | 212 | Database changes are performed automatically as part of deployment process. | 208
Environments | Expert | 213 | Test environments are readily available. Can be reproduced with manual work + coordination between operational teams. | 209,210,211,212
Environments | Expert | 214 | Access to a production-like environment is restricted to a small group of closely-related application teams, and delays at this level are unusual. | 0
Environments | Expert | 215 | Environment provisioning partially automated. | 206
Environments | Expert | 216 | Some virtual environments have interfaces available ‘stubs’ to run end-to-end testing. | 214
Environments | Professional | 217 | Database upgrades and rollbacks are tested with every deployment | 215
Environments | Professional | 218 | Database performance is monitored and optimized. | 215
Environments | Professional | 219 | Minimal manual work is required to replicate and configure environments but this can be completed within hours. | 216
Environments | Professional | 220 | Multiple test environments are readily available for the exclusive use of the team, including a production-like environment that’s allows a reasonable level of non-functional and cross-system integration testing and reliable acceptance testing. | 216
Environments | Professional | 221 | Dev workstations are easily configured and can be built in an automated manner. | 213
Environments | Professional | 222 | Virtual environments have all interfaces available ‘stubs’ to run end-to-end testing | 219
Environments | Master | 223 | Data and environments are treated as code, versioned and frequently re-loaded | 220 221
Environments | Master | 224 | Release to release feedback loop of database performance and deployment process is in place. | 220 221
Environments | Master | 225 | Proactive monitoring is in place with shortest possible time to resolve failure. | 220 221
Environments | Master | 226 | IP is built into the process, including automated deployment, provisioning, configurations and data. Integral part of the build pipeline. | 222 223
Environments | Master | 227 | Environments are managed by the team, the team able to create complete simulated environment on demand | 222 223
Environments | Master | 228 | All environments are managed effectively | 222 223
Environments | Master | 229 | Provisioning is fully automated | 218
Environments | Master | 230 | Main dependencies are simulated across the board | 207
Environments | Master | 231 | Virtualization is used if applicable. | 225
Feature teams | Traveller | 232 | The team doesn’t have all cross-functional and cross-component knowledge and skills to complete end-to-end customer feature. | 0
Feature teams | Traveller | 233 | The team members are not dedicated. | 0
Feature teams | Traveller | 234 | The is a low level of collaboration between team members. | 0
Feature teams | Traveller | 235 | There are multiple handoffs and dependencies on the external teams and stakeholders. | 0
Feature teams | Artisan | 236 | The key skills are part of the team. This includes cross-functional and cross-component skills. | 235,236,237
Feature teams | Artisan | 237 | Handoffs are identified. | 238
Feature teams | Artisan | 238 | Triad is established across three functions, quality, product and technical. Triad is committed to execute a strategy together that gets specific, intended results. | 0
Feature teams | Expert | 239 | The team members are dedicated to the team. | 239
Feature teams | Expert | 240 | Cross-functional and cross-component skills are within the team, the team works on a complete feature, across all components and disciplines (analysis, programming, testing, …) | 239
Feature teams | Expert | 241 | New members are efficiently integrated into feature team. | 239
Feature teams | Expert | 242 | Triad is fully-functioning and not dependent on external validation and external authority. | 241
Feature teams | Expert | 243 | Goals are clearly prioritized and timeously achieved | 0
Feature teams | Professional | 244 | T-shaped skills emerge (team members can perform more than one function) | 242 243 244
Feature teams | Professional | 245 | The team is self-organizing. The team is self-managed and has necessary autonomy to modify the design of their team and/or aspects of the organisational context in which the operate. | 242 243 244
Feature teams | Professional | 246 | Metrics are in place to ensure constant improvement. | 246
Feature teams | Master | 247 | All decision-making is internal to the team, who can make decisions on how to deliver artefacts, and as to quality measures applied to artefacts. | 247 248
Feature teams | Master | 248 | T-shaped skill profile is a majority. | 247 248
Feature teams | Master | 249 | Team is responsible for all aspects of feature delivery, from equipment requisition to production. | 247 248
Feature teams | Master | 250 | Continuous improvement is in place, driven by retrospectives within the team and across the teams | 249